Attachment 6

Work Plan – Component A

SUMMARY

Ending Epidemics Education, Training and Technical Assistance Services RFA

RFA #20760/Internal Program #25-0003

PROJECT NAME: Regional Training Centers – Component A

CONTRACT PERIOD:	From: December 1. 2026	To: November 30, 2031

The Ending Epidemics Education, Training and Technical Assistance Services initiative aims to prepare and maintain a knowledgeable, skilled professional workforce to advance AIDS Institute’s strategic priorities to end preventable epidemics, advance equity, fight stigma and promote health. The Regional Training Centers are responsible for ensuring delivery of educational and training services tailored to meet the unique needs of the health and human services providers throughout their designated region: - Central New York, Finger Lakes and Western New York: including counties of Schoharie, Steuben, Schuyler, Yates, Seneca, Ontario, Livingston, Monroe, Wayne, St. Lawrence, Jefferson, Lewis, Oswego, Oneida, Herkimer, Onondaga, Madison, Cayuga, Chemung, Tioga, Broome, Tompkins, Delaware, Cortland, Chenango, Otsego, Niagara, Orleans, Genesee, Erie, Wyoming, Chautauqua, Cattaraugus, Allegany, Essex, Hamilton, Franklin, and Clinton - New York City (NYC) & Long Island: including the five (5) boroughs of NYC, and counties of Nassau and Suffolk - New York City (NYC), Mid-Hudson & Capital District: including the five (5) boroughs of NYC, and counties of Dutchess, Orange, Putnam, Rockland, Sullivan, Ulster, Westchester, Albany, Greene, Columbia, Rensselaer, Schenectady, Saratoga, Fulton, Montgomery, Warren, and Washington Each Regional Training Center will: - Provide an accessible, stigma-free training environment conducive to adult learning. - Establish a training plan that is informed by the demographic, epidemiological and/or unique social determinants of health profiles of the region and is designed to meet the unique needs of the region. - Provide an array of educational, training and technical assistance services tailored to the region to address health inequities and improve health outcomes on topics related to HIV, viral hepatitis and sexually transmitted infections, sexual health, LGBTQAI+ health and drug user health. - Design marketing and promotional strategies to effectively engage health and human services providers throughout the region in available educational, training and technical assistance services. - Contribute to ensuring the initiative’s portfolio of training curricula remains up-to-date and reflective of evidence-based practices and emerging needs. - Work collaboratively with the AIDS Institute and programs funded under Components B, C, D, and E to achieve the goals of the RFA.

Instructions: For the SFS Work Plan Project Summary, applicants are instructed to insert the Project Summary as listed above. Any additional Project Summary entered in this area will not be considered or scored by reviewers of your application.

Funded applicants will be held to the Objective, Tasks, and Performance Measures listed in Attachment 6: Work Plan - Component A. Applicants are not required to enter any Objectives, Tasks, or Performance Measures into the SFS Work Plan.

Attachment 6 – Work Plan – Component A

DETAIL

| OBJECTIVE | TASKS | PERFORMANCE MEASURES |
| --- | --- | --- |
| 1: Establish a Regional Training Center. | 1.1. Hire and maintain qualified staff to meet the expectations of the program, including staff responsible for program management, training design and delivery, and program administration. | 1.1.1. Qualified Program Manager is in place to provide programmatic and fiscal oversight throughout the contract period. |
|  |  | 1.1.2. Qualified staff are in place to oversee training design and delivery throughout the contract period. |
|  |  | 1.1.3. Administrative staff are in place to support the activities of the training center throughout the contract period. |
|  | 1.2. Ensure access to a pool of qualified training staff and/or consultants that are representatives of the priority audience and communities served. | 1.2.1. Trainers and consultants reflect the learner audience and communities served. |
|  |  | 1.2.2. Resumes/CVs of staff and consultant are submitted to NYSDOH AIDS Institute for approval. |
|  | 1.3. Establish policies and procedures reflective of AIDS Institute best practices to ensure high quality, accurate education and training delivery. | 1.3.1. Regional Training Center policies and procedures describe scheduling, promotion, cancellation, back-up trainers, complaints, documentation, and reconciliation. |
|  | 1.4. Prepare training team, including trainers, consultants and technical production staff. | 1.4.1. The Regional Training Center has a documented policy in place to prepare, support and supervise all members of the training team, including internal quality reviews. |
|  |  | 1.4.2. The Regional Training Center training team is familiar with relevant New York State clinical guidelines and policies and well-versed in the principles of health equity, harm reduction, trauma-informed care, cultural humility, and effective communication. |
|  |  | 1.4.3. All members of the training team can operate all functions of technology used, including webinar platform, or other digital tools. |

| OBJECTIVE | TASKS | PERFORMANCE MEASURES |
| --- | --- | --- |
| 2: Provide an accessible, stigma-free training environment conducive to adult learning. | 2.1. Secure fully equipped, accessible training space for in-person training. | 2.1.1. Training space is available to accommodate at least 35 adult learners and is equipped with current audio/visual technology. |
|  | 2.2. Provide an accessible virtual learning environment with interactive features that can accommodate at least 250 participants. | 2.2.1. Webinar package can accommodate at least 250 participants. |
|  |  | 2.2.2. Virtual learning software includes core interactive features (multimedia sharing, digital whiteboard, polling, breakout rooms, etc.) |
|  | 2.3. Establish policies and procedures to ensure an accessible, stigma-free learning environment. | 2.3.1. The Regional Training Center has policies and procedures in place to ensure an accessible, stigma-free learning environment. |
|  | 2.4. Adhere to Health Literacy Universal Precautions. | 2.4.1. N/A |
| 3: Establish a training plan to meet the unique needs of the region. | 3.1. Assess regional training needs in collaboration with the NYSDOH AIDS Institute. | 3.1. Regional partners, community planning bodies and funded AIDS Institute providers are surveyed annually to identify training needs and priorities. |
|  |  | 3.1.2. Emerging needs are reported in the monthly narrative. |
|  | 3.2. In collaboration with the AIDS Institute and other training providers in the initiative, develop a semi-annual calendar of training events to address identified gaps. | 3.2.1. All trainings are scheduled in the initiative-wide registration system and approved at least six (6) weeks prior to delivery. |
|  |  | 3.2.2. New York State Peer Worker Certification core courses are available within the region. |
|  |  | 3.2.3. Information for scheduled training is accurately posted in the initiative-wide registration system, including location or link, dates, time, etc. |

| OBJECTIVE | TASKS | PERFORMANCE MEASURES |
| --- | --- | --- |
| 4: Provide educational, training and technical assistance services tailored to the region. | 4.1. Deliver a mix of in-person, virtual, blended or other distances learning services (e.g., agency specific requests, tailored trainings, etc.) designed to ensure access throughout the region. | 4.1.1. Deliver a minimum of 500 hours of training, capacity building, or technical assistance activities annually. |
|  |  | 4.1.2. Agency-specific requests are documented in monthly narrative report. |
|  | 4.2. Training events represent a mix of in-person and distance learning formats as well as didactic and skills building opportunities. | 4.2.1. At least 20% of training hours scheduled include in-person skills building opportunities. |
|  |  | 4.2.2. At least 20% of training hours scheduled are delivered virtually. |
|  |  | 4.2.3. 100% of training participant attendance documented and reconciled in the initiative registration system. |
|  | 4.3. Collaborate with the AIDS Institute and/or Component B: Topic-Specific Training Centers of Expertise to provide technical assistance to enhance organizational capacity. | 4.3.1. Up to 20 hours of AIDS Institute-approved technical assistance services are delivered annually. |
|  | 4.4. Collaborate with Component B: Topic-Specific Training Centers of Expertise to provide advanced-level courses within the region. | 4.4.1. The Regional Training Centers host up to three (3) advanced level courses annually with Component B: Topic-Specific Training Centers of Expertise. |
|  |  | 4.4.2 Monthly narrative reports document planning, promotion and outcomes. |
|  | 4.5. Collaborate with Component E: Training Centers for Peer Leadership and Access to Employment Resources, Peer Worker Certification and other professional development. | 4.5.1. Monthly narrative reports document activities to support peer leadership development, New York State Peer Worker Certification and professional development. |
|  | 4.6. Work with the Component D: New York State Peer Worker Certification Academic Center to facilitate awarding New York State Peer Worker Certification and other continuing education credit. | 4.6.1. At least 25% of training hours scheduled support the New York State Peer Worker certification program. |
|  |  | 4.6.2. Continuing education credit is documented as required on training certificates awarded. |

| OBJECTIVE | TASKS | PERFORMANCE MEASURES |
| --- | --- | --- |
| 5: Marketing and promotion | 5.1. Design a cutting-edge marketing strategy to outreach and engage new and existing health and human services providers throughout the region. | 5.1.1. Marketing strategies and outcomes are documented in the monthly narrative. |
|  |  | 5.1.2. Marketing metrics are reviewed annually to improve provider reach. |
|  |  | 5.1.3. New contacts are documented in monthly narrative report. |
|  | 5.2. Outreach to offer of technical assistance and tailored training services to partners within the region. | 5.2.1. Regional outreach strategies are documented in the monthly narrative report. |
|  |  | 5.2.2. Requests for technical assistance and tailored training services are documented in the monthly narrative report. |
|  | 5.3. Facilitate regional networking opportunities to identify and share resources. | 5.3.1. At least one (1) in-person regional networking event is hosted annually to identify emerging needs and share local resources. |
|  | 5.4. Maintain a webpage within the organization website with information about the Regional Training Center, available training and technical assistance services, and a link to the initiative registration. | 5.4.1. Website is live, accurate and up-to-date. |
|  | 5.5. Actively monitor course registration and adjust promotions to ensure at least 20 participants attend each training. | 5.5.1. Attendance of a minimum of 20 participants from the designated audience is documented for each training event. |
|  | 5.6. Communicate registration and all logistical information to participants at least 1-3 weeks and 1-3 days before the training. | 5.6.1. The rate of no-show for registered training participants is less than 30%. |

| OBJECTIVE | TASKS | PERFORMANCE MEASURES |
| --- | --- | --- |
| 6: Training design and review | 6.1. Ensure training curricula remain up to date, revising or developing content as directed by the AIDS Institute. | 6.1.1. Up to eight (8) hours of existing curricula are revised annually; or develop up to eight (8) hours of new curricula to be annually. |
|  | 6.2. Facilitate expert review and/or pilot of new or revised training curricula. | 6.2.1. Feedback is incorporated into training materials as approved by the AIDS Institute. |
|  |  | 6.2.2. All final training materials are approved by AIDS Institute. |
|  |  | 6.2.3. All final training materials are uploaded to Box.com. |
|  | 6.3. Lead and/or participate in Training of Trainers as directed by the AIDS Institute. | 6.3.1. N/A |
| 7: Program monitoring and evaluation | 7.1 Participate in initiative-related meetings and calls with the AIDS Institute. | 7.1.1. Program Manager and Lead training staff attendance at quarterly contractor workgroup calls is documented. |
|  |  | 7.1.2 Program Manager and appropriate training staff attendance at up to two (2) Training of Trainer sessions is documented. |
|  | 7.2. Routinely review program data as it relates to program goals and Work Plan performance measures. | 7.2.1. Continuous quality improvement activities are designed and implemented to address areas for improvement. |
|  |  | 7.2.2. Continuous quality improvement activities are documented in monthly narrative reports, including improvement objective, steps taken and resulting outcomes. |
|  |  | 7.2.3. Satisfactory review during annual AIDS Institute training monitoring. |
|  | 7.3. Participate in routine monitoring activities. | 7.3.1. Program Manager/Lead Trainer participate monthly meetings with AIDS Institute Contract Manager. |
|  |  | 7.3.2. Narrative reports and vouchers are submitted monthly and in a timely manner. |

| OBJECTIVE | TASKS | PERFORMANCE MEASURES |
| --- | --- | --- |
| 8: Flexibility in programming to direct resources effectively | 8.1. Flexibility in programming is necessary to ensure that resources are effectively directed to communities most in need. | 8.1.1. N/A |
|  | 8.2. Contract activities and deliverables may be modified as any point in the contract upon direction of the AIDS Institute to address emerging needs, disparities or to accommodate advances in best practice. | 8.2.1. Assist with non-Work Plan public health issues if/when they arise. |
|  | 8.3. Assist with other priority public health issues if/when they arise as approved by AIDS Institute Contract Manager. | 8.3.1. Assist with non-Work Plan public health issues if/when they arise. |