RFA Number OHEP 2025-01

HEALTH RESEARCH, INC.

New York State Department of Health

Office of Public Health

Division of Public Health Infrastructure

Workplan

Local Health Department Health Equity Contractor

Applicants must complete the following Workplan template. Workplans must demonstrate a clear, logical, and feasible approach to completing each deliverable within the contract period. All components should be internally consistent with alignments between activities, timelines, staffing, and the proposed budget. Incomplete or vague responses, particularly within the Program Approach section, may result in a lower score or disqualification.

Applicants must include the following:

Program Approach: Applicants must describe how the activities will be carried out. This should include methods, strategies, tools, and/or partnerships that will be used to successfully complete the deliverable. The program approach should be specific and detailed enough to understand your process for implementation, not just what will be done.

Staff Name & Title: Identify the individual(s) responsible for completing each activity, including their name and official title. Staff assignments should align with the proposed scope of work and demonstrate appropriate expertise and capacity.

| Deliverable 1: Informational Needs Assessment to Support Prevention Agenda Partnerships |  |  |  |
| --- | --- | --- | --- |
|  | To Be Completed By | Staff Name & Title | Program Approach |
| Activity 1: Develop and submit an informational needs assessment and distribution plan for NYSDOH review and approval that includes: Conduct a stakeholder assessment, such as surveys, interview guides, or focus group, to propose target audiences for the assessment, including local health departments, hospitals, community-based organizations and other relevant Prevention Agenda partners Questions designed to collect information related to: Existing Prevention Agenda resources, tools, training, and informational materials Current partnership and engagement activities Informational and training needs Data utilization practices Incorporation of health equity principles into existing resources and practices Develop and maintain a target audience categorization table that organizes participating organizations by partner type, geographic region, and engagement category Distribute the approved informational needs assessment to identified target audiences Maintain response tracking documentation that includes outreach activities, participation rates, completed responses, and engagement trends across target audience groups Submit response tracking summaries and participation updates to NYSDOH throughout the assessment period | July 30, 2026 |  |  |
| Activity 2: Develop and submit a written summary report of informational needs assessment findings: Compile and summarize information needs assessment responses Develop a written findings report that includes statewide and regional trends, informational and training needs, partnership gaps, data utilization finding, and health equity considerations Submit draft assessment findings and distribution materials to NYSDOH for review and approval Upon approval, distribute finalized informational needs assessment findings to local health departments, hospitals, community-based organizations, and other relevant Prevention Agenda partners | August 15, 2026 |  |  |
| Activity 3: Develop and submit a final recommendations report for NYSDOH Develop a final recommendations report that includes: Priority partnership and capacity-building needs Recommendations to strengthen Prevention Agenda partnerships Recommendations to improve information sharing and communication strategies Recommendations for training and technical assistance opportunities Recommendations to strengthen data utilization and integration of health equity principles into Prevention Agenda implementation activities Submit final recommendation report and supporting documentation to NYSDOH | August 30, 2026 |  |  |

| Deliverable 2: Plan, coordinate and facilitate a one-day in-person meeting for the Prevention Agenda workgroup |  |  |  |
| --- | --- | --- | --- |
|  | To Be Completed By | Staff Name & Title | Program Approach |
| Activity 1: Develop and coordinate materials, and participation for a one-day Prevention Agenda workgroup meeting Develop and submit a detailed workgroup agenda for NYSDOH review and approval Prepare presentation materials, discussion guides, and handout materials summarizing findings from the informational needs assessment. Share all materials developed with NYSDOH Coordinate presenters, stakeholders participants, and meeting communications in collaboration with NYSDOH Coordinate meeting logistics, including venue arrangements, accessibility accommodations, and virtual participation options | September 10, 2026 |  |  |
| Activity 2: Facilitate one-day Prevention Agenda workgroup meeting: Present findings from the informational needs assessment Facilitate structured discussions with NYSDOH program experts and Prevention Agenda stakeholders focused on partnership needs, engagement gaps, health equity considerations, and opportunities for collaboration Manage in-person and virtual participation to support inclusive engagement and participation Document key discussion themes, priorities, recommendations, and action items discussed during the workgroup meeting | September 15, 2026 |  |  |
| Activity 3: Develop and submit a Prevention Agenda workgroup summary report to NYSDOH: Develop a written summary report synthesizing findings from the informational needs assessment and Prevention Agenda workgroup discussions Develop region-specific agenda items and recommendations that reflect localized needs, priorities, partnership gaps, and capacity-building opportunities Develop recommendations to support future regional and statewide Prevention Agenda engagement and partnership strategies Submit final workgroup summary report and supporting documentation to NYSDOH | September 30, 2026 |  |  |

| Deliverable 3: Facilitate 5 in-person Regional Prevention Agenda Partnership Summits |  |  |  |
| --- | --- | --- | --- |
|  | To Be Completed By | Staff Name & Title | Program Approach |
| Activity 1: Develop region-specific summit materials and session content Develop region-specific presentation materials, discussion guides, and session modules informed by: findings from the informational needs assessment; and priorities and recommendations identified during the Prevention Agenda workgroup meeting Submit draft summit materials and agendas to NYSDOH for review and approval | October 1, 2026 |  |  |
| Activity 2: Coordinate and manage logistics for five (5) regional Prevention Agenda Partnership Summits Coordinate and manage logistics for five in-person regional Prevention Agenda Partnership Summits, including: Securing meeting locations in collaboration with NYSDOH, Coordinating accessibility accommodations and virtual participation options, Managing participant outreach, recruitment, registration, and meeting communications in coordination with NYSDOH regional offices, Develop and maintain summit registration and participation records | October 1, 2026 |  |  |
| Activity 3: Facilitate five (5) regional one-day, in-person Prevention Agenda Partnership Summits with virtual participation option: Facilitate five regional one-day, in-person Prevention Agenda Partnership Summits with virtual participation options, as applicable Present standardized, region-specific summit materials and session modules Facilitate structured discussions focused on: Advancing health equity, Addressing social determinants of health, Improving data utilization, Strengthening regional partnerships, Identifying opportunities for Prevention Agenda collaboration Facilitate engagement among local health departments, hospitals, NYSDOH regional offices, community-based organizations, and other community and health partners Document summit discussion themes, partnership priorities, participant feedback, and action items identified during summit activities | November 15, 2026 |  |  |
| Activity 4: Develop and submit a Regional Prevention Agenda Partnership Summit evaluation summary report Develop, distribute, and collect post-event surveys for summit participants Compile and summarize participant feedback related to summit content, delivery, participant experience, partnership readiness, and capacity-building needs Develop a final evaluation summary report that includes: Key findings and regional trends, Identified areas of impact and remaining partnership gaps, Participant feedback and engagement outcomes, Provide recommendations for future Prevention Agenda partnership and capacity-building activities Submit final evaluation summary report and supporting documentation to NYSDOH | November 30, 2026 |  |  |

| Deliverable 4: Develop and submit a comprehensive Prevention Agenda Partnership Evaluation and Implementation Report |  |  |  |
| --- | --- | --- | --- |
|  | To Be Completed By | Staff Name & Title | Program Approach |
| Activity 1: Maintain ongoing project coordination and communication Meet monthly with NYSDOH staff to review project status, timelines, deliverables, and emerging needs Participate in monthly meetings with NYSDOH staff to review project status, deliverables, timelines, implementation progress, and emerging project needs Develop and submit meeting summaries or supporting documentation related to project coordination activities, as requested by NYSDOH | Ongoing |  |  |
| Activity 2: Develop and submit project monitoring summaries Develop and submit monitoring summaries documenting progress toward approved workplans, deliverables, timelines, and project activities Develop and maintain performance tracking documentation related to meetings, assessments, outreach activities, participation metrics, and engagement efforts across all deliverables Develop summaries documenting implementation successes, challenges encountered, lessons learned, and recommendations for continuous improvement | November 30, 2026 |  |  |
| Activity 3: Develop and submit a comprehensive final evaluation and project summary report to NYSDOH: Project Implementation and Outputs: Summary of all project activities and completed deliverables Attendance records and participant reach across meetings, workgroups, and regional summits Description of topics addressed and reported outcomes or changes resulting from project activities Evaluation Findings: Summary of post-event survey findings and other evaluation results Assessments of project effectiveness in meeting stated objectives and advancing Prevention Agenda priorities Identification of key successes, challenges, and implementation lessons learned Reach and Participation Metrics Number of individuals, communities, and regions served Counties and zip codes reached Number and type of collaborative partners Key successes and challenges encountered Plans, if any, to continue project activities beyond the grant period | November 30, 2026 |  |  |